## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new member may need extra time to understand the project | 1 | 2 | 2 | 40 | team leader and all members | 2026-05-14 | Assign smaller tasks first to new member so they can get familiar with before taking on larger work | No new members have joined so far | Close
| Lack of motivation or responsibility | Fall begind on assigned work or not contribute consistently | 3 | 4 | 2 | 12 | team leader and all members | 2026-06-12 | Devide tasks clearly, check progress during the iteration, and adjust ownership early if work is blocked. | The team used assigned SCRUM tasks and shared updates. Some work still needed close follow-up near deadlines. | Close
Communication | duplicate work | Team members may accidentally work on the same task or the same part of a feature without realizing it. | 2 | 3 | 2 | 24 | team leader and all members | 2026-06-13 | Confirm task ownership before coding and use GitHub branches/PRs to show what each person is working on. | Feature branches helped reduce duplicate work. The team continued to confirm ownership in messages. | Close
| worked on wrong components | A member may spend time on the wrong feature, branch, or component and create work that does not match the current iteration goal. | 2 | 3 | 2 | 24 | Feature owner and team lead | 2026-06-09 | Before starting a task, confirm the SCRUM number, branch name, expected fiels, and eacceptance criteria. | This risk appeared when branch ownership was confusing. The team corrected the workflow by pushing to the intended feature branch. | Close
| useless work | Work may be done on something that is not required for the current iteration or final delivery. | 2 | 3 | 2 | 24 | Feature owner and team lead | 2026-06-09 | Stay focused on iteration deliverables and move extra ideas to a futre-work list instead of blocking required work. | The team prioritized core HealthNest features and presentation deliverables over lower-priority additions. | Close
| inconsistent work | Documents, slides, UI pages, or code may be written in inconsistent styles, making the final project look less unified. | 2 | 3 | 2 | 24 | team leader and all members | 2026-05-26 | Review work before submission or merge, keep slide style cosistent, and align UI pages to the same HealthNest visual style. | Dashboards and final presentation sections were reviewed for consistent wording and layout, but final poblish is still being monitored. | Close
Requirements | unclear requirements | Assignment, STD, SPPP, or feature requirements may be misunderstood, causing missing content or incorrect implementation. | 3 | 4 | 2 | 12 | team leader and all members | 2026-06-14 | Review the syllabus, project instructions, grading rubrics, and instructor feedbakc before finalizing each deliverable. | The used the syllabus and instructor QA feedback to guide the doc update and final iteration planning. | Close
| scope creep | Project may be too broad if we treat too many features as essential | 3 | 5 | 3 | 9 | team leader and all members | 2026-06-09 | Focus on essential HealthNest features first, then mark unfinished or optional ideas as future enhancements. | The team narrowed focus to dashboards, lab results, appointments, Pulse AI, testing, and final presentation. | Close
| constant requirements changes | Requirments or expectations may change during development, causing rework and schedule pressure. | 4 | 4 | 3 | 12 | team leader and all members | 2026-06-09 | Discuss requirement changes as a team, update task ownership, and avoid changing finished work unless it affects grading or core functionality | Changes were handled through team discussion and iteration planning. Remaining changes are limited to final polishing and documentations. | Close
Management | improper task assignments | Tasks may not be assigned clearly | 2 | 3 | 2 | 24 | team leader | 2026-06-15 | Assign tasks based on role, feature ownership, and deadline priority; clarify who owns implementation, testing, and documentation. | SCRUM tasks and roles helped organize work. The team continued to clarify ownership when branch or feature scope was unclear. | Close
| improper planning | The team may underestimate how long coding, testing, integration, documentation, and presentation preparation will take. | 2 | 4 | 2 | 16 | team leader and all members | 2026-06-09 | Keep iteration goals realistic, check progress regularly, and finish integration/testing before the final deadline when possible. | Some final-week tasks were compressed, so the team prioritized slides, STD updates, quiz/final prep, and project deliverables by urgency. | Close
| lack of management skills | The team may struggle with coordination, prioritization, or decision-making during a fast project timeline. | 2 | 3 | 2 | 24 | team leader and all members | 2026-06-15 | Keep communication regular and divide reponsibilities clearly | The team lead and members coordinated through shared updates. This risk is reduced but still monitored through final submission. | Close
Technology competence | Not familiar with the framework used | Some members may have limited experience with frameworks | 3 | 4 | 3 | 18 | team leader and all members | 2026-05-19 | Use official documentation, existing project patterns, and teammate review when working in less familiar parts of the stack. | Team members learned the stack while implementing dashboards, appointments, lab results, Pulse AI, and tests. | Close
| Not familiar with the programming language used | Some members may not be equally comfortable with the languages | 3 | 4 | 3 | 18 | team leader and all members | 2026-05-12 | Assign tasks based on familiarity when possible | Frontend and backend work was divided by feature ownership. Test examples helped make unfamiliar syntax easier to follow. | Close
| Not familiar with unit testing | May have limited experience writing unit tests | 3 | 3 | 2 | 18 | team leader and all members | 2026-06-15 | Start with helper-function tests and key component tests, then add backend pytest coverage for important API/skill logic. | Automated tests were added for login, appointments, lab results, and backend appointment/lab skills. More CI integration is still needed. | Close
| Other technology incompetence | Limited experience with Supabase auth/database configuration, environment variables, or deployment setup may create blockers. |  |  |  |  | team leader and all members | 2026-05-19 | Document environment variables, keep local setup instructions updated, and ask teammates to test setup on their machines. | The team used Docker Compose and shared setup guidance. Environment consistency remains a risk during final integration. | Close
| Not familiar with Git | Limited Git experience could lead to some problems | 3 | 3 | 2 | 18 | team leader and all members | 2026-05-19 | Use one feature branch per SCRUM task, check git status before committing, and open PRs from the correct branch. | The team used feature branches such as SCRUM-59, SCRUM-61, and SCRUM-79. Wrong-branch confusion was corrected during the workflow. | Close
Design and implementation | Improper design | The design may not support patient and provider workflows well or may make later changes difficult. | 4 | 5 | 4 | 8 | Feature owners | 2026-06-15 | Review architecture before implementation, keep patient/provider flows separated, and reuse shared API/service patterns. | Dashboards, lab results, appointments, and Pulse AI were organized by role and feature. Design consistency is still reviewed before final delivery. | Close
| improper technology stack | The selected tools or frameworks may not fit the project | 2 | 4 | 3 | 24 | team leader and all members | 2026-06-14 | Choose realistic tools, avoid unnecessary additions, and use existing React/FastAPI/Supabase patterns instead of overengineering. | The team stayed with React/Vite, FastAPI, Supabase, Docker, and GitHub Actions. No major stack replacement was needed. | Close
| Messy code | Code may be difficult to read or maintain | 4 | 4 | 3 | 12 | team leader and all members | 2026-06-12 | Follow shared coding style, keep components/services organized, remove unnecessary logic, and review changes before merging. | Feature files and tests were reviewed during iteration work. Some final cleanup may still be needed before submission. | Close
Testing | Not enough testing | The project may not have enough automated or manual testing to prove that core HealthNest workflows work correctly. | 3 | 4 | 3 | 18 | team leader and all members | 2026-06-13 | Add Jest tests for frontend components and helper logic, pytest tests for backend logic, and manual test cases for major workflows. | Automated and manual tests were added for login, appointments, lab results, and backend skills. Testing coverage is improved but still active. | Close
Integration and deployment | Not enough time for integration and deployment | The team may run out of time to merge, build, test, and record the final demo/presentation. | 3 | 5 | 3 | 9 | team leader and all members | 2026-06-15 | Start integration before the final stage, freeze scope early, run local builds/tests, and keep slides/report updated while coding continues. | Final integration and presentation work were scheduled before the Sunday recording and Monday deliverables. | Close
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.