## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 05/05-05/13 | For this iteration, we finished filling out the SPPP document and familiarized ourselves with all of the required documentation for the project. We also decided on the tech stack we plan to use and made a list of the functional and nonfunctional requirements for the project. | There not any major technical issues that arised besides a minor github push collision that was resolved very quickly | None | So far our processes have been working fairly well, but this is something we'll have to continue working on in future iterations. | 0 | 0 | 0 | 0 | 0 | 40.5 | 33.5 | 2.5 | 9 | 7.5 | 2 | 0 | 0 | 4 | 4.5 | 7.5
1 | 5/14-5/25 | For this iteration, we completed the user onboarding, dashboard UI, lab results, and appointment scheduler features. On the documentation side, we completed the first iteration of the SDD and STD. We also addressed professor feedback on the SPPP. | Minor git conflict caused by the completion of 2 features at the same time. | N/A | Increased communication on when PRs are expected to be raised. | 35 | 0 | 0 | 0 | 0 | 65.5 | 62.5 | 3 | 6.5 | 0.5 | 10 | 27 | 6 | 5.5 | 3.5 | 4.5
2 | 5/26-6/8 | For this iteration, the team made significant progress across multiple core application features. We brought Secure Messaging close to completion, implemented biometric authentication, expanded Pulse AI functionality with additional patient-facing skills, and continued refining appointment scheduling and dashboard features. The team also increased automated testing coverage, performed extensive manual and end-to-end testing, documented discovered defects through GitHub Issues, updated project documentation, and completed the Iteration 2 presentation and supporting deliverables. | Several technical issues were identified through integration and end-to-end testing, including frontend/backend integration bugs, appointment scheduling failures, CI/CD and linting issues, branch management conflicts, and environment configuration problems. Additional effort was required to validate AI features, biometric authentication workflows, and realtime messaging functionality across multiple user scenarios. | Coordinating work across several major features simultaneously required increased communication and planning. Balancing feature development, testing, documentation, issue tracking, and presentation preparation toward the end of the iteration created additional scheduling and workload challenges. | Continue integrating automated and end-to-end testing earlier in the development cycle to identify issues before feature completion. Improve coordination around pull requests, branch management, and feature integration. Maintain detailed issue tracking and testing metrics while continuing to expand automated test coverage for newly developed functionality.
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Aaron | 2026-05-09 | ChatGPT | Assist with Git commands | Accepted | For the most part I was just using it to jog my memory on git commands, but when it generated something I wasn’t familiar with, I asked it to explain. | Here’s the link
Stephanie | 2026-05-10 | ChatGPT | Asked for useful git commands | Accepted | I selected pull, status, and branch from the AI response and rewrote the explanation in my own understanding. | https://chatgpt.com/share/6a022381-bec4-83e8-a11d-da460de5b39f
Deven | 2026-05-12 | Claude (Opus 4.7) | Requirements Analysis | Modified | I used some suggestions and modified it to fit well with our vision. | Below is a refined functional requirements list. I kept your original eight, sharpened some of them, and added requirements that close gaps around HIPAA/compliance, clinical safety, identity, EHR interoperability, and a few workflows that the vision implies but that the current list doesn't cover. Changes and additions are flagged after the list. ## Refined Functional Requirements **Dashboards** FR-01 — Patient Home Dashboard As a patient, I want to view my upcoming appointments, active prescriptions, outstanding bills and insurance claims, recent lab/imaging results, secure messages from my care team, and a prioritized action-item list on a single home page, so that the medical information I need most often is one click away. FR-02 — Doctor Home Dashboard As a doctor, I want to view today's schedule, my inbox (messages, refill requests, results to review), unsigned encounters with age and overdue flags, and a patient quick-lookup field on a single home page, so that all the patient and workload information I need is one click away. FR-03 — Practice Admin Dashboard As a practice administrator, I want to view provider utilization, no-show rates, claim status, and pending patient identity/eligibility verifications, so that I can manage clinic operations without leaving the platform. **AI assistants** FR-04 — Patient-Facing AI Assistant (RAG grounding) As a system, I want to ground a HIPAA-eligible LLM on the patient's records, billing, insurance, and care-team directives via retrieval-augmented generation (no fine-tuning on PHI), so that responses are personalized and auditable without exposing PHI to a non-BAA model provider. FR-05 — Doctor-Facing AI Assistant (RAG + voice) As a doctor, I want a voice-enabled assistant grounded on my schedule, panel, and the active patient's chart, so that I can request information hands-free during clinical work without the model being fine-tuned on patient data. FR-06 — Patient Query Skill As a patient, I want to ask the assistant questions about my medical records, bills, appointments, and prescriptions in text or voice, so that I don't have to navigate the site to find answers. FR-07 — Patient Plain-Language Summarizer Skill As a patient, I want to see doctor directives and clinical notes translated into plain-language summaries with risks and next steps, so that I can act on my care plan without decoding medical jargon. FR-08 — Doctor Visit-Overview Skill As a doctor, I want the assistant to automatically generate a pre-visit summary (recent history, active problems, meds, last labs, open issues) tied to my schedule, so that I am caught up the moment a visit starts without manually prompting. FR-09 — Doctor Ambient Scribe Skill As a doctor, I want the assistant to optionally transcribe the visit and draft an encounter note for my review and signature, so that documentation does not eat into my visit or after-hours time. FR-10 — Clinical Safety Guardrails As a system, I want every AI output that contains clinical guidance to include source citations from the underlying record, a confidence indicator, and a "this is not medical advice — contact your care team" disclaimer on patient-facing surfaces, so that hallucinations and over-reliance are mitigated. FR-11 — AI Escalation Path As a patient, I want the assistant to detect emergencies, suicidal ideation, or out-of-scope questions and route me to 911, a crisis line, or a human staff member, so that I am never left relying on an AI for urgent care. **Scheduling** FR-12 — AI Appointment Scheduler As a patient, I want to request, reschedule, or cancel appointments through the assistant, which negotiates against the provider's real availability, visit-type duration rules, and my own calendar, so that scheduling does not require back-and-forth messages. FR-13 — Scheduling Policy Engine As a practice, I want scheduling decisions to be constrained by deterministic business rules (visit type duration, provider scope, insurance accepted, room/resource availability, buffer time), so that the AI cannot book invalid appointments. FR-14 — Reminders and No-Show Mitigation As a patient, I want automated reminders by my preferred channel (push, SMS, email) with one-tap confirm/reschedule, so that I don't miss appointments. **Identity, access, and consent** FR-15 — Patient Identity Proofing As a system, I want to verify a new patient's identity to at least NIST 800-63 IAL2 before granting record access, so that PHI is not exposed to imposters. FR-16 — Authentication and MFA As any user, I want to sign in with strong authentication including MFA, so that my account and PHI are protected against credential theft. FR-17 — Role-Based Access Control As a system, I want to enforce least-privilege access by role (patient, provider, nurse, billing, admin) and by patient-provider relationship, so that staff only see records relevant to their duties. FR-18 — Proxy and Caregiver Access As a guardian or designated caregiver, I want scoped proxy access to a dependent's chart with documented consent and the ability to revoke, so that I can manage care for minors or family members lawfully. FR-19 — AI Processing Consent As a patient, I want to opt in (or out) of AI processing of my records and visit audio, with granular consent for ambient scribing, summarization, and third-party model use, so that my preferences are respected and HIPAA authorization is documented. FR-20 — Audit Logging As a compliance officer, I want every PHI access, AI inference over PHI, and administrative action logged immutably with user, timestamp, and purpose, so that we can satisfy HIPAA audit and breach-investigation requirements. FR-21 — Break-the-Glass Emergency Access As an authorized clinician, I want to access a chart outside my normal relationship in an emergency with mandatory justification and post-hoc review, so that emergency care is not blocked by access rules. **Interoperability and clinical workflows** FR-22 — EHR Interoperability (FHIR/HL7) As a system, I want to read and write patient data through FHIR R4 (USCDI v3) and HL7 v2 interfaces, so that the platform integrates with existing EHRs and meets 21st Century Cures Act information-blocking rules. FR-23 — Lab and Imaging Result Delivery As a patient, I want to receive lab and imaging results per Cures Act information-blocking rules with optional provider-set hold windows for sensitive results, so that I get my data without violating clinical-safety norms. FR-24 — E-Prescribing and Refill Workflow As a doctor, I want to send and refill prescriptions including controlled substances (EPCS) from the patient chart, so that prescribing happens in-platform. FR-25 — Referral Workflow As a doctor, I want to initiate referrals and share a structured clinical summary with the receiving provider, so that care transitions are tracked and the loop closes. FR-26 — Secure Messaging As any user, I want to send secure, audited messages between patients and care teams with attachment support, so that asynchronous communication happens inside the HIPAA boundary. FR-27 — Telehealth Visits As a patient or doctor, I want to join a HIPAA-compliant video visit from inside the appointment, with the doctor assistant active during the call, so that virtual care uses the same workflow as in-person care. **Billing** FR-28 — Insurance Eligibility and Estimates As a patient, I want to see my insurance coverage, copay, and an out-of-pocket estimate for a scheduled visit, so that I am not surprised by the bill. FR-29 — Bill Pay and Payment Plans As a patient, I want to pay bills, set up payment plans, and dispute charges in-platform, so that billing is part of the same calm experience as care. **Patient data rights** FR-30 — Right of Access and Data Export As a patient, I want to download my full record in a portable format (CCDA + FHIR bundle) and request transmission to a third party, so that I can exercise HIPAA Right of Access. FR-31 — Record Amendment Requests As a patient, I want to request corrections to my record and see the status of that request, so that I can exercise my HIPAA amendment right. **Non-functional adjacent (kept here because they shape feature behavior)** FR-32 — Accessibility and Localization As any user, I want the app to meet WCAG 2.2 AA and offer at least the most common languages spoken in the practice's population, so that the platform is usable by everyone the practice serves. FR-33 — Notifications and Preferences As any user, I want to choose channels, quiet hours, and per-category preferences for notifications, so that the platform stays useful without being noisy. FR-34 — Data Retention and Deletion As a compliance officer, I want configurable retention schedules per record type and a documented destruction process aligned to state and federal record-retention rules, so that we don't keep PHI longer than allowed. --- ## What changed and what's new **Sharpened from your original list** FR-04 / FR-05 replace your "Customized AI Assistant" requirements. I changed "trained on" to "grounded via RAG on" because fine-tuning a model per doctor or per patient is impractical, expensive, and creates a HIPAA nightmare (PHI baked into model weights cannot be deleted on request). Grounding via retrieval is the standard pattern and aligns with what Azure OpenAI, AWS Bedrock, and other BAA-eligible providers actually support. I also made explicit that the model must be HIPAA-eligible with a BAA. FR-08 was tightened: "tracking patient time slots, not prompting" is now "automatically generate a pre-visit summary tied to my schedule." Same intent, less ambiguous for engineering. FR-12 (Scheduler) is now patient-initiated instead of "system-initiated" because two AI agents negotiating with each other without a deterministic source of truth is a feasibility and liability risk. The negotiation happens against a rules engine (FR-13), not between two autonomous agents. **Newly added — compliance** FR-15 to FR-21 cover identity proofing, MFA, RBAC, proxy access, AI consent, audit logging, and break-the-glass — none of which were in the original list and all of which are mandatory for a HIPAA-covered platform handling PHI. FR-19 in particular: if you are sending PHI to a third-party AI model, you need documented patient consent or a HIPAA authorization, plus a BAA with the model vendor. This is the single biggest compliance gap in the original list. FR-30, FR-31, FR-34 cover patient data-rights and retention obligations. **Newly added — clinical safety** FR-10 (guardrails, citations, disclaimers) and FR-11 (escalation/emergency routing) are critical. A patient-facing assistant that translates doctor directives without citations or disclaimers can cause harm if it hallucinates dosage or risk information. Building these in from day one is much easier than retrofitting. **Newly added — interoperability** FR-22 (FHIR/HL7), FR-23 (results delivery per Cures Act), FR-24 (e-prescribing/EPCS), FR-25 (referrals). The vision says "adaptable across any practice" — that is interoperability work, and the original list assumed the data is already in the platform without specifying how it gets there. **Newly added — workflows implied by the vision but not specified** FR-09 (ambient scribe), FR-14 (reminders), FR-26 (secure messaging — referenced in the patient dashboard but not specified anywhere), FR-27 (telehealth), FR-28/FR-29 (billing/eligibility/payments — implied by the patient dashboard's "bills" but not specified), FR-03 (admin dashboard), FR-32 (accessibility/localization), FR-33 (notification preferences). **One thing I deliberately did not add** A "train the doctor assistant on the doctor's voice/style" requirement. It sounds appealing but is a poor fit for a v1 — voice cloning and per-user fine-tuning add cost and risk without clear differentiated value over a well-grounded RAG assistant with good prompts. Worth revisiting after launch. Want me to turn this into a `.md` or `.docx` deliverable in your project folder, or break it down further into MVP vs. post-MVP scope?
Deven | 2026-05-12 | Claude (Opus 4.7) | Cosmetics for Lab 1 | Accepted | I prefilled the word document with my screenshot and answers. I had asked AI to handle the cosmetics of the document, organizing the screenshots and making the font more readable for submission. | Done. The reformatted file is in place — original preserved as a backup. What changed (cosmetics only — verbiage untouched): …
Aaron | 2026-05-13 | ChatGPT | Help decide on high level nonfunctional requirements. | Modified | I started by writing out some ideas then asked ChatGPT to help augment my ideas. I then tried to summarize all of the requirements in my own words, using ChatGPT for help in some places. | Here's the link
Stephanie | 2026-05-13 | ChatGPT | QA Plan | Modified | I asked it for a general idea of what a QA plan should include and what metrics and commonly used to measure whether a project is working properly. I used the suggestion as a reference, then selected and reworte the plan. | Prompt history was deleted by accident, so this is a reconstructed summary. I asked it to explain what should be included in a basic QA plan, especially the metrics, code review process, testing plan, and defect management. It suggested common QA metrics such as completed features, number of test cases, test pass rate, and open defects, along with some other ideas that I did not include because they did not fit our SPPP scope. It also gave examples of how QA can support code review, testing, and bug tracking. I used those ideas as a starting point, then modified the wording and selected the metrics that fit our project, including feature completion, test cases, pass rate, open defects, and summary quality checks.
Stephanie | 5/15-17/2026 | Claude | Figma UI design | Modified | I used AI to suggest realistic wording for different parts of the UI, including dashboard lables, alert messages, text, placeholder text, and healthcare-related examples. | I asked AI to help generate realistic healthcare UI test for a high-fidelity wireframe, including real-world dashboard content, alert messages, appointment reminders, lab result notices, prescription refill alerts, and AI assistant prompt examples. The AI provided sample wroding for provider and patient dashboard cards, system alerts, banners, and placeholder content. I used the ideas as inspiration and adjusted the final wording myself inside the Figma mockup.
Aaron | 2026-05-18 | ChatGPT | Help with lab 2 | Modified | For the functional requirements portion of the lab, my main workflow was to write everything out and then use AI to help with better wording and verify correctness. I used it to confirm the quality of my work, occasionally using it to help with the wording of things For the docker portion, I used AI to help me with the configuration of the project. I had it explain anything I didn’t understand. Once I understood everything, I corrected some of the mistakes made by ai, such as updating the port number in the docker-compose.yml file. | Here's the link
Stephanie | 2026-05-18 | ChatGPT | Assist with Lab 2 | Modified | I ran some commands myself based on the resources I’ve searched online, then asked for verification and some other suggested commands I should use. I started with my own selected entity classes, then used AI to check if anything important was missing. I decided not to add extra classes because I wanted the diagram to stay focused on my two Jira stories. I added only the classes and attributes that matched my design and idea. | https://chatgpt.com/c/6a0b4fb7-953c-83e8-a977-7e9fee33f740 https://chatgpt.com/c/6a0b5d19-7a3c-83e8-a9a4-0a29b444e8ea
Chamarr | 2026-05-18 | ChatGPT | App name ideas | Accepted | I used chat gpt to generate some name ideas for our app. We took those ideas into consideration and may either use one of those names or as inspiration | https://chatgpt.com/share/6a0b9f1d-808c-83ea-ba0c-c5f58a8a7857
Chamarr | 2026-05-20 | ChatGPT | eslint file help | Modified | I ran into an error with eslint, the error was in the file and I used AI to locate the error and give me the solution to solve it. I used most of the file it gave me and changed a little bit of it | https://chatgpt.com/share/6a0e5855-ba6c-83ea-8feb-c91606363221
Aaron | 2026-05-20 | ChatGPT | Assist with Security Design | Modified | I used ChatGPT to help tighten up my wording for the security design portion of our SDD document, also using it to add detail in some places. | Here's the link
Deven | 2025-05-23 | Claude (Opus 4.7) | Lab results feature implementation | Accepted | I used Claude Code to generate boilerplate and deterministic code for the lab results feature. Also used Opus to red-team against my code.
Aaron | 2025-05-23 | Claude Code | Appointment Scheduler implementation | Accepted | I used Claude Code to assist with the appointment scheduling implementation, providing business logic, feedback and specific implementation ideas when necessary. | Here's the link
Stephanie | 2026-05-28 | ChatGPT | Help with git commands | Accepted | I asked AI for help with Git commands, checking my branch, committing Jest test files, pushing to the Appointment Scheduling branch, and understanding the CI/CD failure messages. | Prompt summary: Asked AI how to push Jest test work to the appointment branch, how to format the commit message, and how to understand the failed CI/CD checks. Output summary: AI identified that Jest tests passed locally but CI/CD failed because ESLint did not recognize Jest globals and the mock file. Final result: Git branch was updated and CI/CD passed after fixing the ESLint config.
Stephanie | 2026-05-29 | Claude | Appointment Scheduling frontend Jest test implementation | Modified | I used Claude to suggest test structure, mock setup, component test ideas, and fixes for common Jest issues such as CSS mocking, import.meta.env, React act(...) warnings, and ESLint Jest globals. I selected the actual Appointment Scheduling behaviors to test, reviewed the component code, adjusted mock data and expected text, ran the tests locally, fixed errors, and confirmed the final test results. I also updated the ESLint config so Jest globals and mock files were recognized correctly. | Prompt summary: Asked AI to help write Jest tests for the Appointment Scheduling frontend and make the tests match the project style. Output summary: AI provided test templates and troubleshooting guidance. Final result: Added 5 Jest test suites with 33 passing tests locally, covering helper logic, appointment list display, booking page behavior, appointment modal states, and confirmation modal behavior. CI/CD passed after the ESLint config fix.
Chamarr | 2026-05-30 | Claude | Frontend login Jest test | Modified | I used claude to help write the tests of the login page and to write tests of different edge cases or error catches i may have missed. I also had it test the biometric login feature | Write a Jest test file for a React Login component at frontend/src/__tests__/Login.test.jsx. The component has: Email and password inputs with a show/hide toggle Patient/Provider role selector (defaults to patient) Submit button ("Sign in as Patient/Provider") that calls authApi.signIn({ email, password }) then onSignedIn(session, role) "Continue with passkey" button (outside the form) that calls authApi.signInBiometric(email) then onSignedIn({ user: data.user }) "Create an account" button that calls onSwitchToSignup Error messages on failure, "Signing in…" while loading Imports from ../lib/authApi and ../Login.css Mock ../lib/authApi and ../Login.css. Use @testing-library/react with render, screen, fireEvent, waitFor. Group tests into: Rendering, Role selector, Form interaction, Normal sign in, Biometric sign in. Include an AI usage summary comment at the top.
Stephanie | 2026-05-26 | Claude | Appointment Scheduler and Lab Results Jest test implmentation | Modified | I used ai to suggest mock setup, test cases, and assertion patterns, Modified test to match actual component test, helper functions, and local behavior. | Asked to draft Jest/React testgin library tests for appointment page/modal/cards and lab result upload/review/patient view. Final code was reviewed and adjusted manually.
Chamarr | 2026-05-29 | Claude | Biometric login implementation | Modified | I needed help with the biometric login and whre to start by having AI create the additions to the code and I went in and made the final touches. AI also helped me debug all the errors I encountered | Implement optional WebAuthn/passkey biometric login for the FastAPI + React app while keeping existing email/password auth intact. Backend Add biometric schemas in auth/schemas.py Add routes: /auth/biometric/register/start /register/finish /login/start /login/finish Add service logic in auth/service.py Use webauthn/py_webauthn Store only: credential_id public_key sign_count user/email device metadata Use Supabase tables: biometric_credentials biometric_challenges Frontend Add enableBiometricLogin() and signInBiometric() to authApi.js Add base64url ↔ ArrayBuffer helpers Add: “Continue with passkey” button in Login.jsx “Enable biometric login” button in dashboard/settings Use: navigator.credentials.create() for setup navigator.credentials.get() for login Save session like normal login Acceptance Tests Successful biometric verification → login + correct dashboard Failed/canceled verification → deny access + keep email/password available Keep project structure and existing auth routes unchanged.
Stephanie | 2026-06-02 | ChatGPT | Docter/Patient dashboard Jest test and DFA Visit-Overview planning | Modified | I used ai to plan reasonable dashboard jest coverage and clarify how DFA visit overview should connect to provider workflow. Adjusted based on actual branch structure and feature scope. | Prompt history + output summary: I asked ChatGPT for help planning and writing the Jest/React Testing Library coverage for the Doctor Dashboard and Patient Dashboard branches. The prompts included questions such as which files needed tests, whether one dashboard test file was enough for the branch, how to avoid touching production code, how to check branch status before pushing, how to interpret local test results, and how to fix common test setup issues such as React import/setupTests/eslint warnings. For DoctorDashboard, AI suggested coverage for the dashboard navigation, doctor greeting, summary cards, today's schedule, AI pre-visit summaries, unsigned encounters, patient alerts, profile menu behavior, and sign-out callback. For PatientDashboard, AI suggested coverage for the patient navigation, greeting, main dashboard sections such as appointments/labs/messages, profile menu, and sign-out interaction. The output included proposed test structures, mock patterns for callbacks/API behavior, React Testing Library query suggestions, and short explanations of why each test was relevant to the user story. I modified the AI-generated ideas to match the actual component text and CSS/DOM structure in our codebase, removed or avoided unnecessary personal/test data, adjusted assertions after running the tests locally, and kept the final implementation focused on frontend behavior rather than unrelated backend work. I also asked AI to review whether the branch was ready to push and used the guidance only as a checklist while I made the final decisions and verified the tests locally.
Stephanie | 2026-06-04 | ChatGPT | QA plan and STD updates | Modified | I used AI to understand automated testing coverage expectations, distinguish local Jest/pytest tests from CI/CD regression gates, and rewrite STD sections. Updated wording to reflect actual test scope and limitations. | Prompt summary: Asked what automated testing means for QA lead, what frontend/backend tests should be tracked, and how to document CI/CD and regression testing honestly.
Stephanie | 2026-06-05 | ChatGPT | Iteration 2 presentation slide review and testing metrics | Modified | I used AI to compare the slide deck against the STD and meeting notes. Updated slide content to use verified info from local test output rather than unverified earlier estimates. | Prompt summary: Asked whether the Iteration 2 slides aligned with STD/meeting notes, then shared frontend/backend test output. Final metrics: frontend 191 tests, 189 passed/2 failed; backend 105 passed.
Aaron | 2026-06-01 | ChatGPT | Assistance in implementing Secure Messaging and enhancing appointments | Modified | I used ai to help during the development process. My main workflow was to use Claude to generate a plan for me and ChatGPT to bounce ideas off of about that plan. The two models often had opposing ideas, I used my knowledge about the business logic and direction of our project to make informed decisions about what to do in any given situation. | Here's the link
Aaron | 2026-06-01 | Claude Code | Assistance in implementing Secure Messaging and enhancing appointments | Modified | I used claude to help me with the implementation of Secure Messaging and to enhance Appointmnet Scheduling. I provided the full context of our project so that it could make informed decisions. Most of the time, I asked it to just provide and explain the code and then I added the code to the project, making edits in key areas. Sometimes I also had it write the code to the project and verified it. | Prompt summary: Asked Claude Code to assist with development, testing, debugging, and CI/CD validation for the Secure Messaging and Appointment Scheduling features. Prompts focused on implementing realtime messaging workflows, unread message tracking, provider-patient conversation management, appointment scheduling functionality, provider availability handling, branch management, Jest test creation, and troubleshooting GitHub Actions failures. Output summary: Claude Code generated implementation plans, React and FastAPI code suggestions, Jest/React Testing Library test templates, Supabase integration guidance, realtime subscription patterns, unread count synchronization logic, appointment scheduling refactors, and recommendations for resolving linting, branch tracking, Docker Compose, and CI/CD issues. It also provided guidance on commit workflows, branch cleanup, and debugging frontend state management problems. Final result: Secure Messaging functionality was completed with contact retrieval, conversation threads, realtime message delivery, unread badge tracking, read-status synchronization, and provider-patient messaging workflows. Appointment Scheduling was refactored to support provider availability and appointment management. Additional Jest test coverage was added and refined for related frontend components. Multiple GitHub Actions, ESLint, branch configuration, and Docker Compose issues were resolved, resulting in successful builds and passing CI/CD checks after manual review, testing, and adjustment of the AI-generated code and recommendations.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Chamarr Auber
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
2 | 05/05-05/13 | 10 | 6 | 1 | 1- Reviewed functional and non-functional requirements 2 - Helped determine the tech stack with the team 5 - Discussed roles, tech stack, project idea 6 - I set up the github, CI/CD pipeline, and Jira board and created the epics and introduction stories for the team | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 0 | I did not use any AI at all | I created our github, Jira board, and our ci/cd pipelines I merged our lab1 branch to the main branch I started to created the Epics for the outline and intro stories to keep track | I had a git push collision with another teammate | I pulled their commit, made my edits and pushed it to the lab1 branch | Finish the intro stories and epics and start discussing assigning tasks with the team based off the Jira | 12
3 | 05/14-05/18 | 10 | 8 | 0.5 | 2 - Did some design on the font of the website and worked on creating a name for the web app 3 - Implemented the landing/login page which was our initial commit to the repo 4 - Ran manual acceptance test from the SCRUM-7 jira on the login page 6 - add all FR's to the jira board and assign them their Epics 7 - Addressed comments from professor | 0 | 0 | 0.5 | 5 | 1 | 0 | 1 | 0.5 | I used AI to generate some app name ideas for the team | Created our initial commit and our web apps landing page/login page. I also added all the FR's to the jira board and assigned them all to their respective Epic | Normal development issues with landing page but nothing major | Was able to finish the landing page and solved the errors | Create our automated ci/cd pipeline | 10
4 | 05/19-05/25 | 8 | 7 | 1 | 3 - Updated eslint files and created the ci/cd yml file, Created and implemented the biometric authentication feature that will go in next iteration 6 - Created our automated ci/cd pipeline that runs docker and checks for syntax error. Must pass in order to merge to the main branch. I also connected our commits to the jira board, so everyone can see all commits for a specific jira ticket 7 - Presented iteration 1 slide deck | 0 | 0 | 0 | 5 | 0 | 0 | 1.5 | 0.5 | I did not use any AI at all | Updated ESLint and created CI/CD configuration files, Developed biometric authentication for the next iteration, Built an automated CI/CD pipeline with Docker, | Problems with ESlint configurations | Was able to leverage AI to help with ESlint file for our Cci/cd pipeline | Finish manual testing for biometric authentication. Implement Jest for frontend. Confirm Jira is tracking our commits | 10
5 | 05/26-06/01 | 11 | 10 | 1 | 0 - Learned how to create and code Jest tests 2 - Wrote the design section of the SDD and wrote part of the business logic section of the SDD 3 - Implemented the frontend Jest tests for the login and signup pages 4 - Wrote and tested frontend tests 5- Communicated with the team about upcoming functional requirements for the next iteration | 1 | 0 | 2 | 5 | 4 | 1 | 0 | 0 | I used AI to help with the login and biometric jest frontend tests I also used AI to help me add biometric authentication | Finished the frontend Jest tests for the signup and login page. Worked on the SDD document | I ran into some issues with the frontend tests with overall syntax | I was able to leverage AI to help me fix the syntax | Reconstructure the frontend and work on the E-presciribing workflow | 12
6 | 06/02-06/08 | 13 | 12 | 1 | 1 - Took meeting minutes for this week 3 - Login/signup bug fix implementation and E-prescribing workflow that will go in iteration 3 release and I also re- organized the frontend folder to make it more readable 4 - Recongifured all test files to ensure the new frontend folder changes were made correctly. Debuged any tests that were not working due to the changes 5 - Communicated with the team about important decisions regarding how patients schedule appointments | 0 | 1 | 0 | 8 | 3 | 1 | 0 | 0 | I did not use any AI at all | There was a bug that ocurred for the login/signup page that I fixed. I also started the E- prescribing workflow and the following tests for that which will be included in the next release. I also reconstructed our frontend folder | I ran into a lot of issues with the bug fix and the reconstruction of the frontend folder because of new imports the state of the chosen role on the signup page | I was able to identify the issue for the signup page and was able fix the new imports for the test files | Finish the remaining parts for the E-prescri- bing workflow and the following Jest tests for it. I will also be adding the frontend tests to our ci/cd pipeline so all new changes must pass all frontend tests in order for it to be integrated I will also do any rem- aining tasks that need to be done for the project and prepare to present for the 3rd iteration | 20
7 | 06/09-06/15

## Deven Shah
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Lead, Requirements Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/5-05/13 | 8.5 | 7.5 | 1 | 0 - learn git and explored other patient software related tools (made an account an explored features) 1 - defined high level requirements 6 - set up initial repository | 4 | 3 |  |  |  |  | 0.5 |  | I used claude (opus 4.7) mainly for requirements added for bridging our requirements with the current SOTA. The requirements were taken as inspiration and modified within our own requirements | 1. Write requirements section on SPPP 2. Set up git, commit a test message on git 3. Participate in I0 presentation | 1. Unclear action items | Use Jira and work with the team to clarify and prioritize action items | 1 - Finalize FR and NFR 2 - Help do high level wireframing 3 - Ensure project initialization and setup is completed 5 - Ensure Jira is aligned with requirements | 7
2 | 05/14-05/18 | 8 | 8 | 0 | 1 - broke down the patient dashboard requirement into smaller, more digestible requirements 2 - using class diagrams from requirements, I was able to design high-level database schema 3 - integrated Supabase into our user onboarding flows 7 - addressed Professor's comments in the SPPP |  | 1 | 4 | 2 |  |  |  | 1 | 5 | 1. Wrote Class Diagram and Database Design sections in SDD. 2. Integrated Supabase into our user onboarding flows. Users are now able to sign up and log in to Healthnest. 3. Addressed professor's feedback in SPPP |  |  | 1 - Complete initialization of AI assistant 2 - Kickstart STD document 3 - stabilize group meeting flow | 20
| 05/19-05/25 | 18.5 | 17.5 | 1 | 2 - class diagram, database design, business algorithms (for pulse AI), and REST API in SDD, addressed professor comments in SPPP 3 - Completed end to end database setup, user onboarding flow (signup, signon, signout), and lab results feature 4 - Manually tested completed features against acceptance criterea listed in the respective jira story 5 - team meetings + iteration deliverable management |  |  | 5 | 10 | 2 | 1.5 |  |  | I used Opus 4.7 for deterministic code generation and ideation for design. Code that was directly used is documented in the codebase | 1. Completed database setup, user onboarding, and lab results features for the application 2. Addressed most comments in SPPP 3. Completed class diagram, database design, and most of business algorithms for SDD 4. Sharpened the Iteration 1 goals for slidedeck | I struggle sometimes personally managing multiple deliverables at the same time (timelines/due dates). | In addition to Jira, once deadlines are approaching I started outlining the items in the team chat. This helps me retain the deliverables for me personally, allows teammates to help fill in missing pieces, and may help others who also face a similar problem. | 1 - Complete Pulse AI for patients 2 - Complete backend integration for patient dashboards 3 - Formalize testing oracles for my features and STD | 30
| 05/26-06/01 | 27 | 26 | 1 | 3: Implemented lab results and Pulse patient features. 4: Tested these features both manually and developed test code. 5: Team meetings |  |  |  | 20 | 5 | 1 |  |  | I used AI similar as last iteration (Opus 4.8), but also used for finding ambiguous test cases | Lab Results feature, Pulse patient feature |  |  | 1. END TO END TESTING, 2. Assist with remaining development work | 30
| 06/02-06/08 | 0
| 06/09-06/15 | 0

## Aaron Brown
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Lead, Design and Implementation lead.
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/05-05/13 | 11 | 10 | 0.5 | 0 - Brushed up on my notes from Secure Software Development. Started learning more about the tools in our tech stack. 1 - Defined high level non-functional security requirements. 2 - Decided on tech stack with the team. 5 - Discussed project requirements, decided on team roles and project direction. 6 - Cloned Github repo, created lab1 branch. 7 - Filled out project documents. | 2 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | I used ChatGPT to refresh my memory on git commands. I also used ChatGPT to decide on high level non-functional security requirements. | 1. Wrote non-functional security requirements, management plan, and configuration management plan in SPPP. 2. Created lab 1 branch on Github. 3. Filled in AI usage and Progress Report documents. | 1. I will need to familiarize myself more with our tech stack. 2. I've had to spend some time wrapping my head around all of the documentation but I think it's coming together. | 1. I brush up on my skills with React and FastAPI. 2. I will continue to read through all of the project documentation. | 0 - Brush up on all of the tools in our tech stack. 3 - Start developing the application and try to get a MVP by iteration 1. 5 - Continue to communicate with the team in order to adapt to any complications that arise. 6 - Start to develop the CI/CD pipeline. 7 - Assist in filling out required documents for iteration 1 | 20
2 | 05/14-05/20 | 20 | 20 | 0 | 0 - Refamiliarized myself with React and FastAPI. Also brushed up on security requirements for our application. 1 - Laid out the security design for our application. 2 - Communicated and deliberated about key design decisions. 3 - Scaffolded the application. 5 - Kept in constant contact with my team, messaging everyday about the project. 6 - Setup the initial docker configuration. 7 - Filled out project documents. | 2 | 6 | 2 | 2 | 0 | 3 | 3 | 2 | I used ChatGPT to help me with the initial docker configuration and laying out the security design for the application. | 1. Wrote Security Design. 2. Created Lab 2 branch, scaffolded the application, and created our initial docker configuration. 3. Worked on filling out the documents. | 1. I'm still getting into the workflow for the project with docker and github. 2. Still getting a hold of all of the documentation for the project. | 1. I just need to keep getting the workflows under my fingers. 2. I think that I will have a hold on the documentation once everything is filled out for iteration 1. | 0 - Continue to learn about tech stack. 2 - Solidify the architectural design. 3 - Begin the implementation of appointment scheduling. 4 - Test the implementation of appointment scheduling. 5 - Continue to communicate with the team. 6 - Solidify the configuration of the application. | 20
3 | 05/21-05/27 | 19 | 19 | 0 | 0 - Continued to relearn our tech stack. 2 - Started to implement some of our software design. 3 - Implemented appointment scheduling in the application. 4 - Verified implementation with various manual and automated tests. 5 - Continued constant communication with the team. 6 - Made key decisions configuration features of our application. 7 - Filled out project documentation. | 2 | 0 | 2 | 6 | 2 | 3 | 2 | 2 | I used claude code to help me with the appointment scheduling implementation and chatGPT to assist in filling out certain parts of the documentation. | 1. Implemented Appointment Scheduling. 2. Explained out software architecture in the SDD. 3. Filled out the documentation. | 1. I've been finding it very hard to keep up with this class while working so much. | 1. I've talked to my boss about cutting back on my hours for the remainder of the class so I can give it more of my attention. | 0 - Learn more about implementing specific security features, read into OWASP TOP 10 and HIPAA compliance. 2 - Start to consider the design for out production environment. 3 - Start to implement secure messaging as well as various security features. 4 - Continue automated and manual testing of the application. 5 - Communicate with the team and attend a team meeting if possible. 6 - Start to consider the configuration for our production environment. 7 - Fill out project documentation. | 20
4 | 05/28-06/03 | 26 | 25 | 1 | 0 - Continued learning about React, FastAPI, Supabase, and testing practices relevant to our application architecture. 1 - Analyzed requirements for Secure Messaging and reviewed the impact of database normalization on existing and planned application features. 2 - Updated portions of the application design to support a normalized database structure and accommodate the Secure Messaging workflow. 3 - Implemented the initial Secure Messaging functionality and refactored portions of the application to align with the normalized database schema. Updated related backend models, APIs, and frontend integrations affected by the database changes. 4 - Wrote automated tests for Secure Messaging and verified that existing functionality continued to operate correctly after the database refactor. 5 - Continued regular communication with the team regarding database changes, feature integration, and implementation progress. 6 - Updated database configuration and project structure to support the normalized schema and related application changes. 7 - Filled out project documentation and tracked development progress. | 2 | 2 | 3 | 8 | 3 | 2 | 3 | 2 | I used Claude Code and ChatGPT to assist with Secure Messaging implementation, database normalization, automated testing, and debugging. AI helped generate implementation plans, code suggestions, test templates, database refactoring guidance, and troubleshooting recommendations for GitHub Actions and ESLint issues. I reviewed, modified, and validated all generated code before integrating it into the project. | 1. Implemented the initial Secure Messaging functionality. 2. Normalized the database schema and updated affected backend and frontend components. 3. Added and refined automated tests for Secure Messaging and related application features. 4. Resolved CI/CD, linting, and integration issues resulting from the database and messaging changes. 5. Contributed to project documentation and progress reporting. | 1. Database normalization required updates across multiple layers of the application, increasing implementation complexity. 2. Realtime messaging introduced additional challenges related to state management, unread message tracking, and synchronization. 3. CI/CD failures and ESLint configuration issues slowed integration and testing efforts. | 1. Database refactoring has been completed and integrated into the application architecture. 2. Secure Messaging functionality is operational, with continued refinement and testing planned. 3. CI/CD and linting issues have been resolved, and I will continue monitoring build stability as new features are added. | 3 - Continue refining Secure Messaging and related patient-provider workflows. 4 - Expand automated test coverage and perform regression testing on recently modified features. 5 - Coordinate with the team regarding integration of new functionality and upcoming deliverables. 6 - Continue improving deployment, CI/CD, and environment configuration as needed. 7 - Update project documentation and progress reports. | 20
5 | 06/04-06/10 | 20 | 18 | 2 | 3 - Continued implementation of the Secure Messaging feature, bringing the functionality close to completion and resolving issues discovered during development and integration. 4 - Performed extensive end-to-end testing across major application workflows, including authentication, appointment scheduling, secure messaging, dashboards, and patient/provider interactions. Identified, reproduced, and documented defects through GitHub Issues. 5 - Worked closely with the team to review testing results, discuss discovered issues, prioritize future work, and prepare the Iteration presentation. Collaborated with a teammate to complete and deliver presentation materials. 7 - Updated project documentation, tracked testing progress, and documented defects and enhancement requests through GitHub Issues. | 0 | 0 | 0 | 10 | 3 | 3 | 0 | 2 | I used Claude Code and ChatGPT to assist with finalizing the Secure Messaging feature, debugging application issues, reviewing test results, and preparing presentation materials. AI was used to help troubleshoot CI/CD and configuration issues, review implementation decisions, summarize completed work, and provide feedback on presentation content. All recommendations were reviewed and validated before being incorporated into the project. | 1. Brought the Secure Messaging implementation to near completion. 2. Performed end-to-end testing across major application workflows. 3. Identified and documented numerous defects and enhancement opportunities through GitHub Issues. 4. Assisted in preparing and completing the Iteration presentation. 5. Contributed to project documentation and project review activities. | 1. End-to-end testing uncovered several defects and usability issues across the application. 2. Integrating and validating multiple completed features increased testing and debugging complexity. 3. Some issues required coordination across multiple team members and project components before they could be resolved. | 1. Discovered issues have been documented in GitHub and prioritized for future development. 2. Secure Messaging is nearing completion and will continue to be refined based on testing results. 3. The team will address identified defects and integration issues during the next iteration. | 3 - Complete remaining Secure Messaging enhancements and bug fixes. 4 - Continue end-to-end, regression, and acceptance testing of application features. 5 - Work with the team to prioritize and resolve issues identified during testing. 6 - Support deployment, CI/CD, and environment improvements as needed. 7 - Update project documentation and prepare materials for upcoming deliverables. | 20
6 | 06/11-06/17

## Stephanie Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader, Desgien & Implementation leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/05-05/13 | 11 | 10 | 1 | 0 – learned more about the QA role, QA metrics, and Git 1 – reviewed the project idea, overview, and high-level requirements 5 – discussed roles, tech stack, and project direction with the team 7 – researched similar products, reviewed materials, drafted presentation slides, and presented | 3 | 1.5 |  |  |  | 1 |  | 5.5 | I used ChatGPT to explain technical terms I was not familiar with, especially around the QA role, QA metrics, and risk management, so I could better understand what QA is responsible for. I also asked AI to suggest some useful website resources so I could read more about those topics and better understand them on my own. | 1. Reviewed and refined the SPPP 2. Researched similar healthcare platforms for the related work section 3. Drafted and revised iteration 0 presentation slides 4. Participated in the iteration 0 presentation | 1. Still getting familiar with QA 2. Some project details were still being finalized | 1. Continue learning QA-related responsibilities 2. Confirm open project details with the team 3. Continue revising the SPPP and risk management sections | 1 – refine requirement details for dashboard, summaries, and scheduling 2 – start sketching frontend layout ideas for the patient and doctor dashboards 4 – continue improving the testing and defect management sections 7 – revise the SPPP and supporting documents based on needed | 20
2 | 05/14-05/18 | 20.5 | 19.5 | 1 | 0 - reviewed Iteration 1 document, SDD/STD, learning weekly content 1 - reviewed functional requirements and considered how they connect to Jira stories 2 - worked on frontend/UI design direction, low-fidelity Figma wireframes, and SDD UI design section 5 - attended team meeting, took meeting minutes | 2 | 1 | 15 |  |  | 1.5 |  |  | Used Figma built-in AI tools to help improve high-fidelity UI details, explore better wireframe layout ideas, and reference real-world dashboard typography and spacing patterns. | 1. Took Meeting minutes for the Iteration 1 planning meeting 2. Helped define the frontend/UI design direction for the project 3. Started low-fidelity Figma wireframes for the dashboard, AI assistant, and appointment flow 4. Created high-fidelity Figma wireframes for the doctor/patient dashboard, AI assistant, and appointment flow 5. Contributed to SDD planning | 1. Tried to figure out the best direction for the UI design and how the dashboard/AI assistant flow should be organized 2. Still getting familiar with the QA role and need more time to understand the testing responsibilities | 1. Set a refined UI design in Figma 2. The QA section in the SPPP received several comments, so those sections still need to be reviewed and fixed. I will spend more time understanding QA to better support the STD and testing plan. | 0 - Continue learning QA/testing 1 - Revise QA-related SPPP sections based on professor comments 2 - Refine Figma wireframes for the dashboard and AI assistant flow 3 - Start frontend implementation for the frontend layout | 20
3 | 05/19-05/25 | 20 | 19 | 1 | 0 - Worked on learning and understanding technical concepts. 1 - Reviewed requirements and checked what materials needed to be included. 2 - Refined the doctor dashboard and lab results workflow design. Also planned the lab upload UI style to keep it aligned with the overall HealthNest dashboard design. 3 - Worked on the Patient/Doctor Dashboard frontend and prepared the lab upload UI direction for future implementation. 4 - Worked on the Software Test Document. Focused on manual testing plans for login/sign-up, dashboard routing, and basic user flow verification. Reviewed how testing connects with CI/CD and future unit/integration testing. 5 - Shared the Iteration 1 slides with the team, included demo videos, updated the team on the STD progress, and asked teammates to review or correct anything if needed. 7 - Prepared Iteration 1 presentation content, organized screenshots/demo materials, and helped align the slides with the team’s completed work | 4.5 | 0.5 | 3 | 6 | 2 | 1 |  | 2 | Used ChatGPT to clarify course concepts and technical terms related to testing, CI/CD, SDD/STD documentation, backend integration, and release preparation. I also used AI to refine wording for the Iteration 1 slides, STD content, lab results workflow, lab upload UI direction. AI was used mainly for organization, wording, and checking whether the presentation and documentation matched the work completed during the iteration. | 1. Created and shared the Iteration 1 presentation slides with the team. 2. Added demo videos for the submission requirement 3. Worked on the STD draft and added testing content for login/sign-up, dashboard routing, local Docker verification, CI/CD checks, and future unit/integration testing. 4. Prepared UI direction and asked the team for feedback. 5. Created and included a clear flow diagram for the SDD to show the provider workflow more clearly. | 1. The STD is completed as a draft, but I am not fully sure if the testing direction and test case coverage are correct yet. 2. Some dashboard features are currently UI-focused with mock data, so more backend-connected implementation is still needed. 3. The lab upload UI style still needs refinement and feedback to make sure it aligns with the rest of the design. the design. | 1. Ask teammates to review the STD and correct anything that does not match the expected testing process. 2. Continue frontend/backend integration in the next iteration so dashboard content can move from mock data to backend-driven data. 3. Wait for team feedback on the lab upload UI style before building the remaining parts next week. | 0 - Continue reviewing course concepts and technical terms not familiar with. 1 - Review Iteration 2 expectations and identify which features or workflows need to be prioritized next. 2 - Continue the lab upload UI design and refine any dashboard workflow designs based on team feedback. 3 - Begin or continue frontend work for the lab upload UI and support any implementation tasks if needed. 4 - Revise the STD based on team feedback and expand test cases for dashboard routing, dashboard views, and future integration testing. | 20
4 | 05/26-06/01 | 22 | 21 | 1 | 0 - reviewed frontend testing concepts, Jest/React Testing Library patterns, Vitest/Jest setup, and Git/PR workflow 1 - reviewed Appointment Scheduler and Lab Results user stories/testing expectations to decide what needed coverage 2 - planned test coverage, design scrum58 UI and component/helper test structure for appointment and lab result features 3 - implemented/updated frontend Jest tests for Appointment Scheduler, Lab Results pages, helper functions, and component behavior 4 - ran local test suites, debugged failing/unstable tests, checked rendered UI output, and verified passing suites before reporting status 5 - documented QA updates for Iteration 2 progress | 2 | 1 | 3 | 4 | 9 | 2 |  |  | Used ChatGPT for Git command guidance, branch/PR workflow checks, and QA/test wording. Used AI suggestions to draft test cases and testing-status explanations, then manually compared them against the actual components, adjusted queries/mock data, and ran the tests locally before using the results. | 1. Added/verified frontend Jest coverage for Appointment Scheduler and Lab Results. 2. Implemented DFA Visit Overview Skill 3. Took manual testing | 1. Some tests/features depended on backend availability data and could not fully pass through all manual flows. 2. Needed to ensure automated tests matched the actual rendered UI instead of expected mock labels. | 1. Continue running tests locally before PRs and document failures clearly. 2. Coordinate with feature owner on availability/data issues. 3. Keep testing results aligned with STD and test case. | 0 - Continue reviewing testing/QA expectations 3 - Continue DFA Visit-Overview and dashboard-related work 4 - Run Jest/pytest and update QA results 5 - Continue STD/slides coordination | 25
5 | 06/02-06/08 | 22.5 | 21.5 | 1 | 0 - reviewed instructor feedback on automated testing, AI/RAG evaluation, security, and HIPAA-related concerns 1 - reviewed STD scope, meeting minutes, acceptance tests, and Iteration 2 requirements to align testing documentation 2 - designed/revised Iteration 2 slide structure, testing metrics layout, and Sprint Backlog presentation order 3 - worked on DFA Visit-Overview/dashboard test updates and supported dashboard-related frontend testing work and DFA assistant 4 - ran and verified frontend Jest/backend pytest results, tracked manual TC results, investigated appointment failures, and updated testing metrics 7 - coordinated STD/Iteration 2 slides updates | 1.5 | 1 | 3 | 4 | 9 |  |  | 3 | Used ChatGPT to organize the STD updates, compare the slide deck against the STD/meeting minutes, refine wording for TC008 and test results, troubleshoot Git/test commands, and expand the AI usage log. Final use was modified: I checked the AI output against actual terminal results, replaced estimated test counts with verified Jest/pytest counts, and adjusted slide wording so failed/blocked tests were not overstated | 1. Completed/updated STD testing content for Iteration 2. 2. Built and revised Iteration 2 slides. 3. Verified test result 4. Updated QA metrics and progress report content to match actual results. 5. Completed patient/provider dashboard jest test 6. Implemented DFA Overview, DFA Assistant 7. Updated jest test for signup page and fix appointment test | 1. Frontend Jest still has 2 failing AppointmentPage tests caused by provider-name expectation mismatch. 2. TC008 appointment booking/manual flow issue remained documented with TC009 and TC010 blocked. 3. Need to ensure final slide numbers match actual terminal output instead of older estimated counts. | 1. Keep the frontend Jest failure documented as an isolated test expectation mismatch. 2. Report TC008 clearly as the manual appointment availability issue. 3. Use verified backend pytest count in slides/STD/progress report. 4. Continue improving automated regression coverage in Iteration 3. | 3 - Finalize feature integration and dashboard backend connection 4 - Add Jest + pytest to CI/CD gates and complete final regression testing 5 - Finalize QA reporting, STD updates, and progress documentation 6 - Improve README/setup instructions and prepare final demo test-account workflow | 25
6 | 06/09-06/15