## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new member may need extra time to understand the project | 1 | 2 | 2 | 40 | team leader and all members | 2026-05-14 | Assign smaller tasks first to new member so they can get familiar with before taking on larger work | No new members have joined so far | Close
| Lack of motivation or responsibility | Fall begind on assigned work or not contribute consistently | 3 | 4 | 2 | 12 | team leader and all members |  | Tasks should be divided clearly or make adjustments if needed |  | Open
Communication | duplicate work | May work on the same task without realizing it | 2 | 3 | 2 | 24 | team leader and all members |  | Tasks should be assigned clearly and reviwed |  | Open
| worked on wrong components | May spend time on the wrong feature or section | 2 | 3 | 2 | 24 | team leader and all members |  | Task ownership should be confirmed |  | Open
| useless work | Work may be done on something that is not needed | 2 | 3 | 2 | 24 | team leader and all members |  | Stay focused on the goals for the current iteration |  | Open
| inconsistent work | Write documents or features in inconsistent ways | 2 | 3 | 2 | 24 | team leader and all members |  | Work should be reviewed before submission or merge |  | Open
Requirements | unclear requirements |  | 3 | 4 | 2 | 12 | team leader and all members |  | Requirment should be reviewed and clarified |  | Open
| scope creep | Project may be too broad if we treat too many features as essential | 3 | 5 | 3 | 9 | team leader and all members |  | Focus on essential features first |  | Open
| constant requirements changes | Requirments may keep changing during develoopment | 4 | 4 | 3 | 12 | team leader and all members |  | Requirments changes should be discussed as a team |  | Open
Management | improper task assignments | Tasks may not be assigned clearly | 2 | 3 | 2 | 24 | team leader and all members |  | Tasks should be assigned based on roles |  | Open
| improper planning | May underestimate how long the tasks will take | 2 | 4 | 2 | 16 | team leader and all members |  | Iteration goals should stay realistic and check the progress regularly |  | Open
| lack of management skills |  | 2 | 3 | 2 | 24 | team leader and all members |  | Keep communication regular and divide reponsibilities clearly |  | Open
Technology competence | Not familiar with the framework used | Some members may have limited experience with frameworks | 3 | 4 | 3 | 18 | team leader and all members |  | Use documentation when needed |  | Open
| Not familiar with the programming language used | Some members may not be equally comfortable with the languages | 3 | 4 | 3 | 18 | team leader and all members |  | Assign tasks based on familiarity when possible |  | Open
| Not familiar with unit testing | May have limited experience writing unit tests | 3 | 3 | 2 | 18 | team leader and all members |  | keep it simple and starts with the most important function |  | Open
| Other technology incompetence | [5 empty] | team leader and all members |  |  |  | Open
| Not familiar with Git | Limited Git experience could lead to some problems | 3 | 3 | 2 | 18 | team leader and all members |  |  |  | Open
Design and implementation | Improper design | The design may not support the project well | 4 | 5 | 4 | 8 | team leader and all members |  |  |  | Open
| improper technology stack | The selected tools or frameworks may not fit the project | 2 | 4 | 3 | 24 | team leader and all members |  | Choose realistic stack, avoid unnecessary tools |  | Open
| Messy code | Code may be difficult to read or maintain | 4 | 4 | 3 | 12 | team leader and all members |  | Follow shared coding standard and keep code organized |  | Open
Testing | Not enough testing |  | 3 | 4 | 3 | 18 | team leader and all members |  |  |  | Open
Integration and deployment | Not enough time for integration and deployment |  | 3 | 5 | 3 | 9 | team leader and all members |  | Start integration before the final stage |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.